VOICE RECOGNITION FOR ROBOT CONTROL AIS VRC-4 Integrated Project Team Execution Plan ¦ One-Week Sprint

| KHUSHAL SINGH | RAKA SARKAR | TAIBAZ PATHAN |
| --- | --- | --- |
| ASR & Preprocessing Lead | ROS 2 & Gazebo Integration Lead | Intent & Safety State Machine Lead |
| MacBook + Ubuntu 24 (VM) | Windows + Ubuntu 22.04 (Native) | MacBook + Ubuntu 24 (VM) |

khushal.singh@stud.fra-uas.de  |  raka.sarkar@stud.fra-uas.de  |  taibaz.pathan@stud.fra-uas.de

# 1.  Project Overview

This document is the finalized one-week execution plan for the Voice Recognition for Robot Control (VRC) project. It defines responsibilities, technical decisions, day-by-day tasks, and success criteria for each team member.

## 1.1  Project Goal

Develop a robust, CPU-compatible voice recognition pipeline that integrates with ROS 2 and controls a simulated robot (ROSWITHA) in Gazebo, fully validated without cloud dependencies or real-time microphone streaming.

## 1.2  Measurable Targets

| Target | Value |
| --- | --- |
| Recognition accuracy — clean audio | > 85% |
| Recognition accuracy — heavy noise (SNR 0 dB) | > 70% |
| False activation rate | < 2% |
| End-to-end latency | < 5 seconds |
| Safe command execution (with confirmation) | 100% |
| Test samples evaluated | >= 100 samples |

# 2.  Environment & OS Constraints

| Member | OS (Host) | OS (Dev) | Role |
| --- | --- | --- | --- |
| Khushal | macOS | Ubuntu 24 (VM) | ASR + Preprocessing |
| Raka | Windows | Ubuntu 22.04 (Native) | ROS 2 + Gazebo Integration |
| Taibaz | macOS | Ubuntu 24 (VM) | Intent + State Machine |

IMPORTANT CONSTRAINT: ROS 2 Humble officially supports Ubuntu 22.04, not Ubuntu 24. Ubuntu 24 VMs may encounter binary dependency issues with ROS 2. Final integration and all ROS 2 testing must be performed on Raka's Ubuntu 22.04 machine. Khushal and Taibaz use their VMs for standalone Python module development only.

## 2.1  What to Avoid (All Members)

- GPU-dependent Whisper / CUDA — use CPU mode only

- Real-time microphone streaming — unstable in VMs

- Installing ROS 2 Humble binaries on Ubuntu 24 (for integration work)

- Cloud API dependencies for ASR

## 2.2  Agreed Technical Stack

| Component | Choice |
| --- | --- |
| ASR Engine | faster-whisper (base model, CPU mode) |
| ROS Version | ROS 2 Humble (Ubuntu 22.04) |
| Python Version | Python 3.10 |
| Simulation | Gazebo (empty world baseline) |
| Audio Input Method | Pre-recorded WAV file injection (NO live mic) |
| Fuzzy Matching | rapidfuzz library |
| Confidence Threshold | 0.75 (default), 0.9 for emergency stop bypass |
| Build Tool | colcon |

# 3.  Fixed Command Vocabulary

All team members must use exactly these commands and confirmation tokens throughout the project. No synonyms or variants in the primary pipeline.

| # | Command | Mapped Robot Action |
| --- | --- | --- |
| 1 | move forward | Positive linear.x velocity |
| 2 | move backward | Negative linear.x velocity |
| 3 | turn left | Positive angular.z velocity |
| 4 | turn right | Negative angular.z velocity |
| 5 | stop | Zero all velocities (emergency bypass if conf. > 0.9) |
| C1 | yes | Confirmation token — approve pending command |
| C2 | no | Confirmation token — cancel pending command |

# 4.  System Architecture

The pipeline is modular and separated into three independently testable layers that integrate through ROS 2 topics.

## 4.1  ROS 2 Topic Map

| Topic | Message Type | Publisher → Subscriber |
| --- | --- | --- |
| /audio/raw | Audio | audio_input_node → asr_node |
| /asr/text | String | asr_node → intent_node |
| /asr/intent | String | intent_node → state_machine_node |
| /voice/command | String | state_machine_node → command_node |
| /cmd_vel | Twist | command_node → Gazebo robot |

## 4.2  Safety State Machine

All motion commands pass through a three-state machine before execution. This ensures no accidental robot motion from low-confidence or unconfirmed commands.

| State | Description | Exit Condition |
| --- | --- | --- |
| IDLE | Listening for voice commands. No motion. | Valid command received (conf. >= 0.75) |
| WAITING_CONFIRMATION | Command identified. Awaiting YES or NO from user. | YES, NO, or 5-second timeout |
| EXECUTING | Confirmed command dispatched to /cmd_vel. | Command complete, return to IDLE |

Emergency Stop Override: If 'stop' is recognized with confidence >= 0.9, the state machine bypasses WAITING_CONFIRMATION and publishes zero velocity immediately.

Timeout Behavior: If no YES/NO confirmation is received within 5 seconds, the state machine returns to IDLE and discards the pending command. No motion is executed.

## 4.3  Project Folder Structure

| Path | Owner / Purpose |
| --- | --- |
| ros2_ws/src/vrc_system/ | Raka — ROS 2 package: nodes, launch, config |
| asr_module/ | Khushal — faster-whisper engine, VAD, normalization |
| intent_module/ | Taibaz — fuzzy matcher, vocabulary, state machine |
| audio_dataset/ | Shared — clean + augmented WAV files, metadata.csv |
| evaluation/ | Shared — batch runner, metrics, confusion matrix |
| docs/ | Shared — diagrams, report assets, slides |
| scripts/ | Shared — setup.sh, build.sh, run_pipeline.sh |

# 5.  7-Day Execution Roadmap

DAY 1 — Environment Setup & Agreement (All Together)

Everyone works in sync on Day 1 to ensure a consistent baseline before parallel development begins.

### All Members Must Install

- ROS 2 Humble (Raka: native; Khushal/Taibaz: skip ROS on VM — Python modules only)

- Python 3.10

- faster-whisper, pyaudio, soundfile, numpy, pandas, rapidfuzz

- Gazebo + colcon (Raka only)

### Day 1 Agreements — Lock In Before Day 2

- Final command vocabulary confirmed (5 commands listed in Section 3)

- Whisper model: base (CPU safe, good accuracy trade-off)

- Confidence threshold: 0.75 default / 0.9 emergency stop

- Audio format: 16 kHz mono WAV

- Output JSON schema agreed:

{ "text": "move forward", "confidence": 0.87, "latency": 2.3 }

- GitHub repo created, folder structure initialized

### Day 1 Deliverable

- All systems can run Python 3.10 + faster-whisper

- All members can transcribe at least one WAV file locally

- ROS 2 running on Raka's Ubuntu 22.04 machine

DAYS 2–3 — Parallel Development Phase

Each member works independently on their module. Daily sync check-in recommended (15 min).

KHUSHAL — ASR & Preprocessing Module Tasks: - Install faster-whisper in CPU mode; confirm model loads without CUDA - Build asr_engine.py: accepts WAV path, returns JSON with text, confidence, latency - Build audio_preprocessing.py: 16 kHz resampling, amplitude normalization, energy-based VAD - Build noise_augmentation.py: mix clean speech with noise at 20 dB, 10 dB, 0 dB SNR - Record/collect 40 clean audio samples (4+ speakers, 5 commands each minimum) - Generate 40 noisy augmented samples using noise_augmentation.py Files to deliver by end of Day 3: - asr_module/asr_engine.py - asr_module/preprocessing/normalize.py + vad.py - asr_module/augmentation/snr_mixer.py - audio_dataset/clean/ (40 files) + audio_dataset/augmented/ (40 files) - audio_dataset/metadata.csv

TAIBAZ — Intent Mapper & State Machine Module Tasks: - Build vocabulary.py with COMMANDS and CONFIRMATION lists - Build fuzzy_matcher.py using rapidfuzz — maps raw ASR text to fixed vocabulary - Build intent_mapper.py: keyword matching + fuzzy fallback, returns intent + confidence - Build state_machine/states.py: IDLE, WAITING_CONFIRMATION, EXECUTING - Build state_machine/transitions.py: all valid state changes with conditions - Build confirmation_logic.py: YES/NO parsing, 5-sec timeout logic, emergency stop bypass - Create intent_module/config.yaml with threshold values Files to deliver by end of Day 3: - intent_module/intent_mapper.py - intent_module/fuzzy_matcher.py + vocabulary.py - intent_module/state_machine/states.py + transitions.py + confirmation_logic.py - intent_module/config.yaml

RAKA — ROS 2 Package & Gazebo Integration Tasks: - Set up ROSWITHA robot model in Gazebo with /cmd_vel subscriber verified - Create ROS 2 package vrc_system with package.xml, setup.py, setup.cfg - Write audio_input_node.py: reads WAV file, publishes to /audio/raw - Write asr_node.py: subscribes /audio/raw, calls asr_engine, publishes to /asr/text - Write intent_node.py: subscribes /asr/text, calls intent_mapper, publishes to /asr/intent - Write state_machine_node.py: wraps state machine logic, publishes to /voice/command - Write command_node.py + cmd_vel_publisher.py: converts intent to Twist, publishes /cmd_vel - Write asr_pipeline.launch.py and gazebo_integration.launch.py - Create ros2_ws/src/vrc_system/config/commands.yaml and parameters.yaml Files to deliver by end of Day 3: - Complete ros2_ws/src/vrc_system/ ROS 2 package - Both launch files working - Gazebo simulation loading ROSWITHA in an empty world

DAY 4 — Full Pipeline Integration (All Together)

This is the most critical day. All three modules are connected end-to-end for the first time. Run from Raka's Ubuntu 22.04 machine.

### Integration Steps (in order)

- Confirm all modules run independently on Raka's machine

- Connect: audio_input_node → asr_node → intent_node → state_machine_node → command_node → /cmd_vel

- Inject pre-recorded WAV files using audio_input_node.py (no microphone)

- Validate each integration checkpoint with the checklist below

### Day 4 Validation Checklist

| Test | Status |
| --- | --- |
| 'move forward' audio file → robot moves forward in Gazebo | [ ] |
| Confirmation prompt appears before motion executes | [ ] |
| 'no' response cancels command — robot stays still | [ ] |
| 5-second timeout with no response → returns to IDLE, no motion | [ ] |
| High-confidence 'stop' (>0.9) bypasses confirmation, stops robot | [ ] |
| Low-confidence audio (<0.75) is rejected — no command issued | [ ] |

### Day 4 Deliverable

- First fully working end-to-end demo recorded (screen capture)

- Integration issues documented in GitHub Issues for Day 5 fixes

DAY 5 — Evaluation & Metrics

Run the full 100-sample evaluation suite and collect all performance metrics for the report.

| Member | Task | Output |
| --- | --- | --- |
| Khushal | Run 100-sample batch test using batch_test_runner.py across all noise conditions | evaluation/results/raw_logs/ + processed_metrics.csv |
| Taibaz | Calculate accuracy per condition, false activation rate, per-command confusion matrix | Completed metrics tables ready for report |
| Raka | Measure end-to-end latency (timestamp at audio publish vs. /cmd_vel publish) | Latency statistics table in evaluation/results/ |

### Target Metrics Table (fill in from results)

| Condition | Accuracy (%) | False Activation (%) | Avg. Latency (s) |
| --- | --- | --- | --- |
| Clean (no noise) | — | — | — |
| Light noise (SNR 20 dB) | — | — | — |
| Moderate noise (SNR 10 dB) | — | — | — |
| Heavy noise (SNR 0 dB) | — | — | — |

DAY 6 — Documentation & Diagrams

| Member | Writing Section | Diagrams |
| --- | --- | --- |
| Khushal | ASR System Design + Evaluation Results section | Data flow diagram (audio → ASR → command → sim) |
| Taibaz | Methodology + Safety State Machine section | State machine diagram with all transitions & timeouts |
| Raka | ROS 2 Setup + Gazebo Integration section | ROS 2 node graph + Gazebo architecture diagram |

### Required Diagrams (all 4 must be created)

- ROS 2 node graph (nodes, topics, publishers, subscribers)

- State machine diagram (IDLE → WAITING_CONFIRMATION → EXECUTING with all transitions)

- Data flow diagram (audio input → ASR → intent → command → simulation)

- Gazebo integration architecture diagram

DAY 7 — Finalization & Submission

| Member | Finalization Task |
| --- | --- |
| Khushal | Final code review of asr_module/, add docstrings, push to GitHub |
| Taibaz | Final code review of intent_module/, write conclusion summary (1-2 pages) |
| Raka | Clean ros2_ws/, finalize README and Integration Guide, create release tag on GitHub |
| All | Assemble final PDF report (15–25 pages), review presentation slides (15–20 slides) |

### Day 7 Final Submission Checklist

| Deliverable | Status |
| --- | --- |
| GitHub repo: clean code, README, no build artifacts | [ ] |
| Final technical report (PDF + DOCX, 15–25 pages) | [ ] |
| Integration guide for ROSWITHA deployment | [ ] |
| All 4 required diagrams in docs/diagrams/ | [ ] |
| Evaluation CSV logs in evaluation/results/ | [ ] |
| Presentation slides (15–20 slides) | [ ] |
| Conclusion summary (1–2 pages) | [ ] |
| Gazebo demo recording / screenshot evidence | [ ] |

# 6.  Final Success Criteria

| Criterion | Target |
| --- | --- |
| 5 core commands recognized and dispatched correctly in Gazebo | > 85% |
| Confirmation state machine working (yes/no/timeout) | 100% |
| 100 test samples evaluated and logged | 100 samples |
| Clean audio recognition accuracy | > 85% |
| Heavy noise accuracy (SNR 0 dB) | > 70% |
| False activation rate on noise/OOV audio | < 2% |
| End-to-end latency | < 5 sec |
| Working Gazebo simulation demo | Required |
| Full ROS 2 package with launch files and config | Required |
| Technical report (15+ pages) submitted | Required |

# 7.  Risk Management

| Risk | Likelihood | Mitigation Strategy |
| --- | --- | --- |
| ROS 2 binary issues on Ubuntu 24 | HIGH | All ROS integration runs on Raka's Ubuntu 22.04 |
| VM audio instability / microphone not working | HIGH | Use pre-recorded WAV injection only — no live mic |
| Whisper too slow on CPU | MEDIUM | Use 'base' model; profile early on Day 2 and switch to 'tiny' if needed |
| Gazebo simulation crash / instability | MEDIUM | Keep world simple (empty); avoid complex physics |
| Integration fails on Day 4 | MEDIUM | Each module has standalone tests; isolate failure point quickly |
| Insufficient audio samples (< 100 test cases) | LOW | Khushal generates augmented samples programmatically on Day 2 |

# References

- Radford, A., et al. (2022). Robust Speech Recognition via Large-Scale Weak Supervision. arXiv:2212.04356.

- OpenAI. (2022). Whisper GitHub Repository. https://github.com/openai/whisper

- ROS 2. (2024). ROS 2 Humble Documentation. https://docs.ros.org/en/humble/

- Ko, T., et al. (2015). Audio Augmentation for Speech Recognition. INTERSPEECH, 3586-3590.

- SYSTRAN. (2024). Faster-Whisper GitHub Repository. https://github.com/SYSTRAN/faster-whisper

- Gazebo Simulation. (2024). Gazebo Documentation. https://gazebosim.org/